## README
Last Update | 2019-10-16
Author | Timothy Koo / Vivek Amatya / Darun Seethammagari / Spyridon Catechis / Het Trivedi
Email | tkoo005@ucr.edu / vamat001@ucr.edu / dseet001@ucr.edu / scate002@ucr.edu / htriv001@ucr.edu
Description | This is the SCRUM document for team 16's CS180 project.
Summary / Requirements | This spreadsheet serves two purposes: (1) for your team to track progress during your sprints, and (2) as a record of what user stories were implemented, in which tasks, and by whom. For (1), if you prefer to use an alternate tool to track progress as you go (e.g., Trello), that is fine. However, for (2), it is critical that you keep the "Product Backlog" and "Archives" up to date, at least at the end of each sprint. Also, note that if the number of estimated points for a story ends up being very inaccurate (i.e., if the user story took much more or much less effort than expected), please update the story points estimate and give a comment explaining the adjustment.
Tabs | Notes
"Product Backlog" | Should be initialized with the user stories and their estimated efforts (i.e., story points)
Depending on the amount of story points, some stories may need to be split into smaller stories
Add "Acceptance Criteria" to each user story by "insert note" to a spreadsheet cell (right click the cell)
"Acceptance Criteria" define what it means to be "Done"
"Task Board" | "To Do" is initialized with tasks defined during the Sprint Planning Meeting (i.e., sprint backlog)
Tasks are expected to have similar sizes, each with a time cost of roughly 3-4 hours
Add "Details" and "Acceptance Criteria" to a task by "insert note" to a spreadsheet cell (right click the cell)
Perform task assignments at the Sprint Planning Meeting
During a sprint, members who become available can pull tasks from the "To Do" list by moving them to "In Progress" and attaching his/her name
Inform your teammates know before you pull a task from "To Do" list
"To Verify" should be pulled by a different team member; This is a good time to perform code review and unit testing
A task in "Done" list should have its verifier's name appended
"Archives" | At the end of a Sprint, finished tasks are moved to "Archives"; Unfinished tasks are moved to the next Sprint Planning Meeting
"Burndown Chart" | At the end of a Sprint, update the "Burndown Chart"
if "Story Points (Remaining)" is above the "Ideal", it would be an indicator for slow progress

## Product Backlog
ID | Story Name | Story (small features) | Story Points | Priority | Comments
1 | School email authentication | As an unregistered user who is insterested in the app, I want to register an account so that I can login the app using my school email | 3 | 1
2 | Email verification | As a user who just submitted my account setup information on the sign up page, I want an email verification to be sent to my RMail address to confirm my signup | 3 | 2
3 | Navbar | As a general user, I would like to have the ability to navigate the site through a navigation bar | 3 | 3
3 | Create new account | As an unregistered user who is insterested in the app, I want to click the sign up button to create a new account | 3 | 4
4 | Log in | As a registered user, I want to click on the log in/vote button that will bring me to a page where I can enter my account name(email address) and password | 3 | 5
5 | Referendums | As a general user, I’d like to see the list of positions which are being up for vote. I’d like to see what department the position is for and also a description of the job. I’d also like to see the list of referendums as well as what they will do. | 4 | 6
6 | Candidates and Position Information | As a general user, I want to click on the candidates button on the navbar that will lead me to a page that contains the responsibilities and tasks of each position and who is running for each. I’d like to see their name, major, year, picture. | 5 | 7
7 | Forms | As a general user, I'd like to click on the forms button on the navbar and be taken to a page with all the forms | 2 | 8
8 | Timeline | As a general user, I would like to see the timeline of the elections on the home page | 3 | 9
9 | Voting Form | As a registered user I would like to go to click on the vote button which will take me to a voting form. I’d like to visually see when I make a selection. I’d like to see how many people I can vote for as well as how many votes I have left. I should also see a visual indication showing that I cannot vote for any more people (such as greying out their profiles). I should be able to change my vote during the voting process. | 5 | 10
10 | Applying to be a Candidate | As a voter, I’d like to receive an email when voting concludes with the winners of the elections. I’d like to see their information, position, and if I voted for them. I should also see the referendums which passed and their description. | 3 | 12
11 | Current # of votes | As a general user, I’d like to see statistics on the number of current votes. | 4 | 13
12 | Admin Portal | As an admin, I would like to see all candidate applications and requests and be able to accept or reject them. I would also like to see all referendums and be able to create, edit, or delete them. | 3 | 14
| Total |  | 44

## Task Board
Backlog | In Progress | Testing | Done
Task 14: Current # of votes
Task 13: Revise Positions and candidates
Task 16: Admin Portal
Task 15: Applying to be a candidate

## Archives
Sprint ID | Scrum Master | Tasks Completed
1 | Het | Task 1: UCR email authentication
1 | Vivek | Task 3: Navbar
1 | Spyro | Task 2: Email Verification
1 | Tim | Task 4: Landing Page
2 | Tim | Task 12: Forms Page
2 | Darun | Task 9: Format Database
2 | Vivek | Task 11: Referendums Page
2 | Het and Darun | Task 7: Voting Form(Tab navigation, display candidates, connect to database)
2 | Darun | Task 10: Timeline
1 | Het | Task 5: Create new account
2 | Spyro | Task 6: Positions and candidates
3 | Tim | Task 13: Revise candidates
3 | Darun | Task 14: Current # of votes
3 | Spyro | Task 15: Applying to be a candidate
3 | Het | Task 16: Admin Portal
3 | Vivek | Task 17: Combine positions into candidates

## Burndown Chart
Sprint ID | Story Points (Total) | Story Points (Completed) | Story Points (Accumulated) | Story Points (Remaining) | Ideal
0 | 44 | 0 | 0 | 44 | 44
1 | 44 | 9 | 9 | 35 | 30
2 | 44 | 23 | 32 | 12 | 15
3 | 44 | 12 | 44 | 0 | 0